## Defect_tracker
SI No | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status (Open/Closed) | Remarks
1 | 2026-02-06 | Raw dataset contained missing values and duplicate records, affecting initial cleaning results | Sprint 1 | Backend Team | Data Quality | Applied missing value imputation, removed duplicates, and revalidated cleaned dataset | 2026-02-07 | Closed | Cleaned dataset verified successfully
2 | 2026-02-08 | time_stamp column was not in proper datetime format, causing time-series sorting issues | Sprint 1 | Backend Team | Formatting | Converted time_stamp to datetime format and standardized date parsing logic | 2026-02-09 | Closed | Chronological ordering corrected
3 | 2026-02-17 | Lag feature generation created null values in early rows, reducing model-ready records | Sprint 2 | Backend Team | Feature Engineering | Handled lag-induced nulls and filtered invalid rows after feature creation | 2026-02-18 | Closed | Feature engineered dataset stabilized
4 | 2026-02-20 | Categorical encoding mismatch created duplicate or missing one-hot encoded columns | Sprint 2 | Backend Team | Encoding | Standardized region and service_type encoding logic before final export | 2026-02-21 | Closed | Encoded schema aligned with training pipeline
5 | 2026-03-01 | XGBoost training failed due to object datatype columns in input features | Sprint 3 | Backend Team | Model Training | Converted unsupported object fields to numeric/encoded features before fitting model | 2026-03-02 | Closed | XGBoost training completed successfully
6 | 2026-03-03 | Saved model path loaded feature_list instead of trained model during deployment testing | Sprint 3 | Backend Team | Integration | Separated model and feature list loading with correct file paths and validation checks | 2026-03-04 | Closed | Prediction pipeline restored
7 | 2026-03-05 | Feature mismatch between training schema and deployment input caused missing column errors | Sprint 3 | Backend Team | Schema Alignment | Aligned deployment input with saved feature list and added missing columns with default values | 2026-03-06 | Closed | Inference compatibility ensured
8 | 2026-03-10 | Streamlit dashboard heading and layout were not properly aligned for presentation view | Sprint 4 | Frontend Team | UI/UX | Adjusted CSS spacing, panel layout, and theme styling for full dashboard visibility | 2026-03-11 | Closed | Dashboard presentation improved
9 | 2026-03-12 | Audit log was not updating correctly after multiple forecast runs | Sprint 4 | Backend Team | Logging | Fixed append logic and timestamp handling in streamlit_prediction_log.csv workflow | 2026-03-13 | Closed | Forecast history recorded correctly
10 | 2026-03-14 | Risk visuals and business charts were insufficient for mentor demo expectations | Sprint 4 | Frontend Team | Visualization | Added KPI badges, executive summary, heatmap, waste trend, and service comparison charts | 2026-03-15 | Closed | Dashboard became demo-ready and interactive